## Week 1
Sprint Name: | Week 1
Goal: | Create a working command line application that supports CRUD operations for an Employee Management Sytem using Core Java.
Tasks:
Task 1 | Describe the project architecture with UML Structural and Behavioural diagrams.
Status: | TODO
SubTask 1 | Create the Use Case Diagram of Employee Management System
SubTask 2 | Create Activity Diagrams of the system
a) Employee Login
b) Admin Add Employee
c) Employee Timesheet Entry
SubTask 3 | Create EMS Class Diagram
SubTask 4 | Create Sequence Diagrams of :
a) Employee Login
b) Admin Add Employee
c) Employee Timesheet Entry
Done: | UML model project uploaded to Git repo in pdf format.
Task 2 | Create a Maven project in Eclipse.
Status: | TODO
SubTask 1 | Write up the dependencies in the pom.xml for a Java application.
SubTask 2 | Include the JUnit5 dependency.
SubTask 3 | Add JaCoCo Maven Plug-in for code coverage.
Done: | Scaffold project showing in eclipse workspace.
Task 3 | Implement the Java application using the TDD approach
Status: | TODO
SubTask 1 | Write the initial test cases using JUnit5.Use Mockito to mock the database.
SubTask 2 | Create the java classes according to the UML model defined along with the associated methods for JDBC operations.
Done: | Passing JUnit test cases
Task 4 | Create the Entity Relationship (ER) Diagram.
Status: | TODO
SubTask 1 | Create the database tables, constraints and relationships between tables.
SubTask 2 | Load sample data in to the database
SubTask 3 | Connect to the database using JDBC
SubTask 4 | Create the Command Line interface with the Scanner class to retrieve user input and display the results.
Done: | A working CLI application according to specifications.
Task 5 | Check code into BitBucket
Status: | TODO
SubTask 1 | Push the code base to the appropriate Bitbucket repository
Done: | Project artifacts and code available and upto date in the repository.

## Week 2
Sprint Name: | Week 2
Goal: | Enhance the CLI application with user friendly error messages
Tasks:
Task 1 | Upgrade the Maven project to factor in error handling and DAO classes
Status: | TODO
SubTask 1 | Follow the TDD approach to refactoring the application to include exception handling for each CRUD operation. Create a custom exception class to handle business logic errors.
SubTask 2 | Create classes and interfaces for the Employee, Timesheet and Login modules.
SubTask 3 | Create a DAO class and interface for each module - Employee, Timesheet and Login
SubTask 4 | Implement Employee, Timesheet and Login classes to use the corresponding DAO to perform CRUD operations
Done: | Upgraded working CLI application.
Task 2 | BDD Using Cucumber
Status: | TODO
SubTask 1 | Use behavior-driven development (BDD) to define clear, unambiguous requirements
SubTask 2 | Turn these requirements into automated acceptance tests.
Done: | Verification of application’s behavior
Documentation of each feature
Task 3 | Update Architecture Diagrams
Status: | TODO
SubTask 1 | Changes to the code base needs to be reflected in the UML class and sequence diagrams.
Done: | Updated project documentation
Task 4 | Check code into BitBucket
Status: | TODO
SubTask 1 | Push the code base to the appropriate Bitbucket repository
Done: | Project artifacts and code available and upto date in the repository.

## Week 3
Sprint Name: | Week 3
Goal: | Introduce JPA with Hibernate and REST APIs for CRUD operations
Tasks:
Task 1 | Update the Maven pom
Status: | TODO
SubTask 1 | Add the dependencies for Web Application development in the pom.xml .
SubTask 2 | Add the JPA and Hibernate dependencies.
SubTask 3 | Remove the JDBC dependencies.
Done: | Project configured for JSPs, Servlets and JPA with Hibernate.
Task 2 | Create REST APIs for the CRUD operations.
Status: | TODO
SubTask 1 | Use JAX-RS to create the REST APIs for CRUD operations.
SubTask 2 | Test the APIs in Postman.
Done: | REST APIs tested successfully in Postman.
Task 3 | Refactor to use JPA with Hibernate for database operations
Status: | TODO
SubTask 1 | Follow the TDD approach to refactoring the application to use JPA with Hibernate instead of JDBC.
SubTask 2 | Write the JUnit test cases for the refactored Java classes.
SubTask 3 | Use @Spy to mock the database implementation class.
SubTask 4 | Implement the refactored classes according to specifications.
Done: | Application successfully connects to the database.
Passing test cases.
Task 4 | Create a Performance Test Plan in JMeter
Status: | TODO
SubTask 1 | Do a performance analysis of the web application for 1000 users
Done: | JMeter shows the test result in Graph format.
Task 5 | Update Architecture Diagrams
Status: | TODO
SubTask 1 | Changes to the code base needs to be reflected in the UML class and sequence diagrams.
Done: | Updated project documentation
Task 6 | Check code into BitBucket
Status: | TODO
SubTask 1 | Push the code base to the appropriate Bitbucket repository
Done: | Project artifacts and code available and upto date in the repository.

## Week 4
Sprint Name: | Week 4
Goal: | Create the backend tier for the EMS using Spring Boot with REST and Data JPA
Tasks:
Task 1 | Update the Maven pom
Status: | TODO
SubTask 1 | Add the dependencies for Spring MVC, Data JPA ,Bean Validator Reference Implementation and Database Connector.
SubTask 2 | Remove the JPA and Hibernate dependencies.
SubTask 3 | (Optional) You may add other dependencies like Lombok to ease the burden of writing boilerplate code.
Done: | Project configured for Spring MVC with REST and Data JPA.
Task 2 | Create the REST Endpoints for the CRUD operations
Status: | TODO
SubTask 1 | Follow the TDD approach to creating the back end tier. You will still be writing the test cases using JUnit but using the framework support in Spring Boot. You need to cover unit tests that can run in isolation as well as integration tests that will bootstrap Spring context before executing tests.
SubTask 2 | The following classes of tests need to be implemented:- a)Smoke and Sanity test:-. Check if the Spring Context is running. b)System test:- It will test the complete application. c)Integration test:- Test the Controller tier together with the Service layer. d)JPA test:- Test the Service tier and the database.
SubTask 3 | Create the Controller, Service and Repository tiers.
SubTask 4 | Create RESTful Web Service endpoints corresponding to each CRUD operation in the Controller tier.
SubTask 5 | Use Status Codes in Error Handling
SubTask 6 | Implement global exception handling with @ControllerAdvice for Controller classes.
SubTask 7 | Use the JSR 380 and implement Validation on the model objects.
Done: | Successfully test the REST API endpoints in Postman.
Task 3 | Refactor to use Spring Data JPA with Hibernate for database operations
Status: | TODO
SubTask 1 | Follow the TDD approach to refactoring the application to use Spring Data JPA with Hibernate.Write the test cases using JUnit but using the framework support in Spring Boot.
SubTask 2 | The following classes of tests also need to be implemented:- a) Smoke and Sanity test:-. Check if the Spring Context is running. b) System test:- It will test the complete application. c) Integration test:- Test the Controller tier together with the Service layer. d) JPA test:- Test the Service tier and the database.
SubTask 3 | Create the Controller, Service and Repository tiers.
SubTask 4 | Create RESTful Web Service endpoints corresponding to each CRUD operation in the Controller tier.
SubTask 5 | Implement global exception handling with @ControllerAdvice for Controller classes.
SubTask 6 | Use the JSR 380 and implement Validation on the model objects.
Done: | REST APIs successfully tested in Postman.
Task 4 | Create a FreeStyle project in Jenkins to automate the workflow
Status: | TODO
SubTask 1 | Create a Jenkins FreeStyle project
SubTask 2 | Checkout/clone the code base from Git repo
SubTask 3 | Compile and package the application
SubTask 4 | Run the JUnit tests and publish the results
Done: | Build executed successfully in Jenkins with passing test cases
Task 5 | Update Architecture Diagrams
Status: | TODO
SubTask 1 | Changes to the code base needs to be reflected in the UML class and sequence diagrams.
Done: | Updated project documentation
Task 6 | Check code into BitBucket
Status: | TODO
SubTask 1 | Push the code base to the appropriate Bitbucket repository
Done: | Project artifacts and code available and upto date in the repository.

## Week 5
Sprint Name: | Week 5
Goal: | Create the Frontend for the EMS using React, Dockerize the application and Refactor to use Microservices
Tasks:
Task 1 | Create a React Project in Visual Studio Code
Status: | TODO
SubTask 1 | Follow TDD with Jest to build the complete front end using React, HTML5 and CSS3.
SubTask 2 | Consume the REST APIs in the Spring Boot-REST-Data JPA back end from your React application using AXIOS.
SubTask 3 | The following screens need to be developed: a) Login Page(may be a single page for both Admins and Employees or separate) b) Forgot Password (may be a single page for both Admins and Employees or separate) c) Admin Add Employee The Admin Add Employee screen should have an option to select a CSV file for bulk upload of employees’ details into the database. d) Admin List Employees g) Employee Timesheet Entry h) Employee View Timesheets i) Search Feature
SubTask 4 | Introduce a 3 second delay into the application when the list of records is being retrieved, or when a record is being updated or added.
SubTask 5 | The pages displaying the list of records and update a record should show a Spinner or Progress Bar while the page is being displayed or the records are being retrieved. The Spinner or Progress Bar should disappear when the page is rendered.
SubTask 6 | The page(s) where a record is added or updated should have the Save/Update button disabled while a new record is being saved or updated. The label on the button should change from 'Save' to 'Saving..'.
SubTask 7 | On successful save or update, the user should only then be navigated to the list of records.
SubTask 8 | On unsuccessful save or update, the user should remain on the page. An notification should be displayed with a user friendly error message.
SubTask 9 | On Delete, the user must immediately be navigated to the list of records(Optimistic Deletes) unless the Delete buttons are on the same page; in which case the page simply needs to be reloaded to display the updated list.
SubTask 10 | The notification for an unsuccessful Create,Update or Delete action will not have a display interval. It will need to be manually closed by the end user.
SubTask 11 | Use Toast Notifications or SweetAlert or any library of your choosing to display alerts and messages to a user. It can be a success message, warning message, or custom message. You may set the display interval to 2-3 seconds.
SubTask 12 | Develop the production server of your react app with Node.js
Done: | Full featured working application deployed with an Express.js server.
Task 2 | Create the Dockerfile environments
Status: | TODO
SubTask 1 | Define the Docker environments using Dockerfile.
SubTask 2 | Create the Dockerfile for the Spring Boot app.
SubTask 3 | Deploy the React app behind an nginx server.
SubTask 4 | Create the docker-compose.yml configuration
SubTask 5 | Run the complete stack with docker compose
Done: | React Application Served With NGINX and Docker
Task 3 | Use Spring Cloud Microservices and Spring Boot Framework to make this application distributed.
Status: | TODO
SubTask 1 | Register the spring boot application with the eureka discovery server.
SubTask 2 | Setup Front End React App to make requests to the NGINX server which acts as a reverse proxy.
SubTask 3 | Allow NGINX server to redirect the requests to Zuul API Gateway.
SubTask 4 | Zuul will route the requests to microservice based on the URL route.
SubTask 5 | Zuul also registers with eureka and gets the IP/domain from eureka for the microservice while routing the request.
SubTask 6 | Change Zuul's load-balancing strategy to any other Netflix Ribbon strategy
Done: | EMS refactored to Microservices application
Task 5 | Update Architecture Diagrams
Status: | TODO
SubTask 1 | Changes to the code base needs to be reflected in the UML class and sequence diagrams.
SubTask 2 | Create the Deployment diagram for the refactored Microservices EMS.
Done: | Updated project documentation
Task 6 | Check code into BitBucket
Status: | TODO
SubTask 1 | Push the code base to the appropriate Bitbucket repository
Done: | Project artifacts and code available and upto date in the repository.